BAS 475 Final Group Project Plan

Connor Davis, Ryan Brennan, John Moore

Wednesday April 27th – Plan project out, assign duties (Connor)

Thursday April 28th – Set up GitHub for everyone and get some initial work done on data (ALL)

Friday April 29th – Continue to work on data, start gathering resources for Presentation (ALL on Data, Connor on Presentation)

Sunday May 1st – Create and finish presentation (and record if needed) (ALL)

Monday May 2nd – Start working on predictions for new data (ALL)

Tuesday May 3rd – Finish working on predictions (ALL)

Wednesday May 4th – Review and turn in presentation and turn in predictions. (ALL)

\*\*Meetings will take place over zoom

\*Project Complete by 11:59pm Wednesday May 4th